## Guidance
Lifecycle Management Methodology Tailoring Plan Guidance
Guidance
The LMM Tailoring process should be completed during development of the project charter, with LMM tailoring decisions captured within that charter. In addition, along with the WBS Dict-Tailoring Plan (Tailoring Plan), the project team should submit the Investment Request (IR), the high-level project schedule, the Work Breakdown Structure (WBS) and Risk Register to the LMM Project mailbox at LMM@ed.gov. These documents constitute inputs to the Tailoring Package. Templates can be found via the LMM SharePoint Site at https://fsa.share.ed.gov/lmm. The LMM WBS Dictionary and Tailoring Plan is an Excel-based tool to help FSA’s Project Managers from the business units, the Technology Office, and the ePMO to collaboratively execute the tailoring processes for their projects. The goals of using this tool are to determine: (1) The Project Risk Tier Rating (Tier I, Tier II, or Tier III) of the project; (2) The applicability of the LMM Artifacts to the project; (3) How the acceptance criteria detailing the intent of that artifact will or will not be met; and (4) Stage Gate preparation and execution and Lessons Learned activities. Before beginning to fill in the tailoring plan tab, take a few moments to familiarize yourself with the descriptions of the various plan inputs available on the Descriptions tab. After the LMM WBS Dict-Tailoring Plan tab is completed, the assigned PM will submit it, along with the rest of the Tailoring Plan Package (i.e. Tailoring Plan, Investment Request, high-level project schedule, and Work Breakdown Structure), to the LMM Tailoring Plan Review Team at LMM@ed.gov. The review team will then schedule a meeting, during which both teams will work together to establish a final tailoring plan for the project.
Resources:
LMM SharePoint Library
Project Management Toolkit
Technology Office Standards Library

## WBS
1 | Project Management | 2 | Acquisition | 3 | Security and Privacy | 4 | Requirements | 5 | Development | 6 | Testing | 7 | Implementation | 8 | Post-Implementation
1.1 | Project Initiation Artifacts | 2.1 | Acquisition Strategy | 3.1 | Information System Security Officer Appointment Letter | 4.1 | Initiative Vision Document | 5.1 | Configuration Management Plan | 6.1 | Master Test Plan | 7.1 | Implementation/ Transition Management Plan Artifacts | 8.1 | Operational Analysis
1.1.1 | Investment Request | 2.2 | Pre-Award Artifacts | 3.2 | Privacy Artifacts | 4.2 | Requirements Management Plan | 5.2 | Preliminary Design Document | 6.2 | Test Suites | 7.1.1 | Implementation Plan | 8.2 | Retirement and Disposal Artifacts
1.1.2 | Business Case/Exhibit 300 | 2.2.1 | Statement of Need | 3.2.1 | Privacy Threshold Analysis | 4.3 | High Level Requirements Document | 5.3 | Detailed Design Document | 6.3 | Test Reports | 7.1.2 | Transition Management Plan | 8.2.1 | System Retirement Plan
1.1.3 | Project Charter | 2.2.2 | Market Research Report | 3.2.2 | Privacy Impact Assessment | 4.4 | User Interface (UI) Specification Document | 5.4 | Solution Source Code and Deployable Packages | 6.3.1 | User Acceptance Test Summary Report | 7.2 | Training Plan | 8.2.2 | System Disposal Plan
1.2 | Project Management Plan Artifacts | 2.2.3 | Acquisition Plan | 3.2.3 | System of Records Notice (SORN) | 4.5 | Detailed Requirements Document | 5.5 | Solution User Manual | 6.3.2 | Test Summary Report | 7.3 | Operations and Maintenance Plan | 8.3 | Technical Stage Gate 5: Retirement and Disposal Review Briefing
1.2.1 | Lifecycle Management Methodology (LMM) Work Breakdown Structure Dictionary and Tailoring Plan | 2.2.4 | Statement of Objectives or Performance Work Statement | 3.3 | External Data Exchange Artifacts | 4.6 | Requirements Traceability Matrix | 5.6 | Release Version Description Document | 6.3.3 | Defect Management Report | 7.4 | Technical Stage Gate 4: Production Readiness Review Briefing
1.2.2 | Scope Management Plan | 2.2.5 | Source Selection Plan | 3.3.1 | Memorandum of Understanding | 4.7 | Data Migration Plan | 5.7 | Technical Stage Gates 1A and 1B: Engineering Review Board (ERB) Review Briefing
1.2.3 | Cost Management Plan | 2.2.6 | Solicitation | 3.3.2 | Computer Matching Agreement | 4.8 | Technical Stage Gate 3: Requirements Review Briefing | 5.8 | Technical Stage Gate 2: Test Readiness Review Briefing
1.2.4 | Risk Management Plan | 2.3 | Post-Award Artifacts | 3.3.3 | Interconnection Security Agreement (ISA)
1.2.5 | Quality Management Plan | 2.3.1 | Contract | 3.4 | Continuity of Services Artifacts
1.2.6 | Resource Management Plan | 2.3.2 | Performance Monitoring Plan | 3.4.1 | Business Impact Analysis (BIA)
1.2.7 | Schedule Management Plan |  |  | 3.4.2 | Information Technology (IT) Contingency Plan (Includes Test Plan)
1.2.8 | Communication Management Plan |  |  | 3.4.3 | Contingency Test Plan Results
1.2.9 | This Artifact has been Removed. |  |  | 3.4.4 | Disaster Recovery Plan
1.2.10 | Independent Verification and Validation Plan |  |  | 3.5 | System Security Documentation Artifacts
1.2.11 | Performance Management Plan |  |  | 3.5.1 | Data Sensitivity Worksheet
1.3 | Project Monitoring Artifacts |  |  | 3.5.2 | System Boundary Template (System Authorization Boundary)
1.3.1 | Performance Reports |  |  | 3.5.3 | System Security Plan
1.3.2 | Baseline Change Control Report |  |  | 3.6 | Security Risk Assessment Artifacts
1.3.3 | Lessons Learned Reports |  |  | 3.6.1 | Security Assessment Plan
1.3.4 | Cost Estimate and Spend Report |  |  | 3.6.2 | System Security Documentation Checklists
1.3.5 | Risk Log |  |  | 3.6.3 | Security Assessment Report
1.3.6 | Project Schedule |  |  | 3.6.4 | Plans of Actions and Milestones (POAMs)
1.3.7 | Action and Issue Log |  |  | 3.6.5 | This Artifact has been Removed.
1.4 | Management Stage Gate 1: Investment Review Briefing |  |  | 3.7 | Authority to Operate Letter and Briefing
1.5 | Management Stage Gate 2: Requirements Review Briefing |  |  | 3.8 | This Artifact has been Removed.
1.6 | Management Stage Gate 3: Project Closeout Review Briefing |  |  | 3.9 | Data Retention Schedule

## WBS Dict Descriptions
eWBS Dictionary and Lifecycle Management Methodology Tailoring Plan Template Input Descriptions
Name | Description
Date of Plan | (Input Date) Enter the date the Tailoring Plan is being prepared. With each version, the date should also change.
Project Identification - Name | (Text Input) Type in the project name and any other necessary identification information.
SDLC | (Drop-down: Waterfall, Prototype, Spiral, Staged / Iterative, Hybrid, COTS, Rapid Application Development, Agile, Scrum, Other) The Software Development Lifecycle that the developer (vendor or internal) will be using for the project. For descriptions of each SDLC see Appendix C of the LMM.
PMO Project Risk Tier | (Drop-down: 1-Complex, 2-Standard, 3-Simple) The Tier is indiciative of the complexity and cost of the project. Tier 1 (Complex) projects last more than 18 months and cost more than $1 million dollars; Tier 2 (Standard) projects take between 6 months to 18 months to complete and cost between $500,000 and $1 million dollars; and Tier 3 (Simple) projects cost less than $500,000 and lasts less than 6 months. For more information, go to http://mystartingline.ed.gov/s/pmotoolkit/.
WBS Code | Artifact number. Sub-documents within artifact groupings are sub-numbered.
Element Name | Name of each artifact and documents within artifact groupings.
Definition | Definition of each artifact and documents within artifact groupings.
Lifecycle Stage | The lifecycle stage during which that artifact starts to be created.
Activities | The functions and actions to be performed during the creation of the artifact.
SME | Subject Matter Expert is the individual who maintains ownership over the artifact or artifact groupings. The SME is responsible for updating artifacts, providing guidance on tailoring individual projects, and participating during Stage Gates and reviews.
SME Organization | The organization under which the Subject Matter Expert is assigned.
Responsible Role | Role responsible for completing artifacts, or documents within artifact groupings.
Applies to Project? | (Drop-down: Creating Document, Updating Existing Document, Part of Another Document, or Not Applicable) This column captures how the project team will meet the acceptance criteria. Specific information regarding the document addressing the intent including the name, version and date should be included under Column L, "If applies, how will intent be met?..."
If applies, how will intent be met? If does not apply, why? | (Text Input) If applies to project, note whether the exact artifact will be created or the intent will be covered by another artifact(s) and how. (WBS ID Number, Project Schedule ID Number, whether artifact resides inside a General Support System (GSS) and requires updating, etc.) If this artifact does not apply to this project, explain why.
Acceptance Criteria | Lists the acceptance criteria any variations from LMM standard must meet to be approved by the LMM team or SME. Criteria must be met in order to obtain approval for LMM standard variance.

## WBS Dict-Tailoring Plan
Lifecycle Management Methodology (LMM) Work Breakdown Structure Dictionary and Tailoring Plan Template | [11 empty] | Enter Date of Plan | DD/MM/YYYY
[12 empty] | Enter Approval Date of Plan | DD/MM/YYYY
Project Name: [Full Name, no acronyms] |  |  |  | Click here for link to LMM Library | [5 empty] | SDLC -> | Select development methodology | PMO project risk tier ---> | Select risk tier
WBS Code | Element Name | Definition | Lifecycle Stage | Activities | Subject Matter Expert | SME Organization | *Responsible Role | Project Point of Contact | Template/Guidance | Applies to Project? | Please note specific name of artifact, version and date. If not applicable, please explain. | Acceptance Criteria
1 | PROJECT MANAGEMENT
1.1 | PROJECT INITIATION ARTIFACTS
1.1.1 | Investment Request | Document that describes the high level scope, cost, schedule for initial approval and funding. | Vision | Define scope, estimate costs and determine high level schedule. | Bobby Estep | IMG | Program Manager/ Senior PM |  | Template |  |  | All fields have been completed and checked for quality and accuracy.
1.1.2 | Business Case/Exhibit 300 | The business case provides details on budget and cost estimate, milestones, alternatives analysis, contracts, performance metrics, and service components. | Vision | Estimate costs, perform an analysis of alternative technical solutions, plan the acquisition, determine performance measures for operational system, describe enterprise architecture components, determine milestone schedule. | Steve Wingard | ePMO | Program Manager/ Senior PM |  |  |  |  | All fields have been completed and checked for quality and accuracy.
1.1.3 | Project Charter | Document that identifies the project scope, objectives, roles and responsibilities, constraints, assumptions, risks and project deliverables. The project charter authorizes the project to be allocated resources and begin work. | Vision | Develop scope statement, identify constraints, assumptions and risks. Determine team members and roles and responsibilities. | Daria Adams | ePMO | Senior PM |  |  |  |  | IMGnature of sponsors, project manager and the Enterprise PMO indicating acceptance.
1.2 | PROJECT MANAGEMENT PLAN ARTIFACTS | The Project Management Plan Artifacts describe the overall approach to manage the project. Tailoring guidance: For tier 3 and some tier 2 projects many of the sub-plans may be combined. Please see the PMO for guidance. | Vision | Develop sub-plans and ensure integration. | [7 empty] | All sub-plans are developed and adequately address how scope, cost, time, resources, quality, communications, acquisition, risk and change will be managed. The Plan has been accepted by the sponsor.
1.2.1 | Lifecycle Management Methodology (LMM) Work Breakdown Structure Dictionary and Tailoring Plan | The Lifecycle Management Methodology (LMM) Work Breakdown Structure Dictionary and Tailoring Plan provides information about how the LMM Artifacts pertain to the project. This also contributes to determining which Project Risk Tier Rating to assign the project. | Vision | Assess the applicability of each LMM Artifact to the project. If an artifact will not be entirely developed or an alternative vendor template is used, define how the acceptance criteria will be met. Projects that leverage vendor support should focus on linking project documents to the established FSA success criteria. Utilize SME resources to clarify expectations. Finalize and submit the draft tailoring plan package (consisting of the tailoring plan, Investment Request, high-level project schedule, and Work Breakdown Structure), with a request for a tailoring meeting, to the LMM Tailoring Team. Once the IPT meets with the LMM Tailoring Team, a decision will be made regarding whether to approve the tailoring plan. | Daria Adams | ePMO | Senior PM |  | Guidance |  |  | This document has effectively conveyed whether each LMM Artifact will apply to the project, and for the artifacts that do not apply, adequately explains the reasons. For artifacts that will not be fully developed, acceptance criteria must detail how the intent of those artifacts will still be met. The LMM Tailoring Team has approved the tailoring plan.
1.2.2 | Scope Management Plan | The Scope Management Plan includes a scope statement, WBS and a description about how scope will be managed and controlled. | Vision | Create scope statement, WBS, WBS Dictionary and change procedures. | Daria Adams | ePMO | Senior PM |  | Guidance |  |  | WBS includes entire scope of the project and a procedure for scope management is identified. The sponsor has accepted the plan.
1.2.3 | Cost Management Plan | The Cost Management Plan clearly defines how the costs on a project will be managed throughout the project’s lifecycle. It sets the format and standards by which the project costs are measured, reported and controlled. The Cost Management Plan identifies who is responsible for managing costs, who has the authority to approve changes to the project or its budget, and how cost performance is quantitatively measured and reported. | Vision | Document cost management process and roles and responsibilities. Develop cost estimate. | Daria Adams | ePMO | Senior PM |  | Guidance |  |  | All aspects of cost management are included in the plan, the sponsor has accepted the plan.
1.2.4 | Risk Management Plan | The Risk Management Plan describes how risks are identified and analyzed, and how risks will be managed throughout the project. It describes how risks are quantified. It includes a risk log and mitigation plans when appropriate. | Vision | Document how risks will be identified, analyzed and managed. Identify risks, analyze and assign quantifiable values to each, and develop risk mitigation plans per the process described in the Risk Management Plan. | Daria Adams | ePMO | Senior PM |  | Guidance |  |  | Definitions of risk ratings are described, all categories of risk have been assessed, and all risks have owners and mitigation plans as appropriate. The risk management plan defines monitoring metrics and a risk monitoring approach. The sponsor has accepted the plan.
1.2.5 | Quality Management Plan | The Quality Management Plan describes the activities and tasks required to deliver the scope of the project while focusing on achieving customer's quality expectations. The Plan identifies which quality standards are relevant to the project and determines how can they be satisfied. It includes the implementation of quality events such as peer reviews, checklists and independent validation and verification. | Vision | Determine quality standards and document the process by which quality will be measured and by whom. | Mike Rockis | TO | Senior PM |  | Guidance |  |  | The plan documents how quality will be managed on the project and includes defined quality control metrics, quality objectives and defines a process for conducting quality assurance reviews for proposed deliverables. The sponsor has accepted the plan.
1.2.6 | Resource Management Plan | The Resource Management Plan describes the type of human resources needed to complete a project. It includes skills needed, when they are needed and in what quantity. It describes how resources will be secured and managed. | Vision | Determine what knowledge, skills and abilities are needed to execute the project and when they are needed. Determine if any training is needed. Document how resources will be secured and managed. | Daria Adams | ePMO | Senior PM |  | Guidance |  |  | The plan documents what type of skills are needed and when and from which organization. It describes how resources will be managed for the duration of the project. The sponsor has accepted the plan.
1.2.7 | Schedule Management Plan | The Schedule Management Plan describes the scheduling process, scheduling responsibilities, important milestones, constraints and assumptions, and how the schedule will be managed, maintained and changed. | Vision | Document how the schedule will be planned, developed, and maintained. | Daria Adams | ePMO | Senior PM |  | Guidance |  |  | The plan adequately documents the schedule process and responsibilities.The sponsor has accepted the plan.
1.2.8 | Communication Management Plan | This Communications Management Plan describes stakeholders and how the project will ensure timely and appropriate generation, collection, distribution, storage, retrieval, and ultimate disposition of project information. | Vision | Conduct stakeholder analysis, develop appropriate communication plans to meet stakeholder needs. Document how and where project information will be stored. | Daria Adams | ePMO | Senior PM |  |  |  |  | All stakeholders are identified, communication activities are identified, and a process for communicating is documented. The sponsor has accepted the plan.
1.2.9 | This Artifact has been Removed. | [7 empty] | Template
1.2.10 | Independent Verification and Validation (IV&V) Plan | The Independent Verification and Validation (IV&V) Plan describes the activities performed by the IV&V team. The Plan identifies the IV&V needs for the project, how IV&V will be executed, which standards will be used, and the specific activities that IV&V will target. IV&V is a component of the Quality Assurance strategy for the project and the IV&V Plan will integrate with the overall Quality Assurance Plan. Note: IV&V is only performed on large and complex projects. | Vision | Determine the IV&V needs and approach for the project. Describe how the approach will be executed and how findings/results will be reported. Note: IV&V is independent of the project team and must report to project sponsors through an independent reporting chain. All FSA IV&V teams report through the Technology Office's QA Program to ensure that independence is maintained. | Trey Wiesenburg | Enterprise Quality & Technical Change Management Group | IV&V Coordinator |  | NA |  |  | The plan documents how IV&V will be managed on the project and includes the activities that IV&V will perform in support of the project. FSA's TO IV&V Coordinator has accepted the plan.
1.2.11 | Performance Management Plan | This plan includes activities to ensure that goals are consistently being met in an effective and efficient manner. | Vision | A performance measurement baseline is established at the beginning of the project. An integrated scope-schedule-cost plan for the project work is compared to measure and manage performance. | Daria Adams | ePMO | Senior PM |  | Template |  |  | Establish performance measurement baseline. Approve integrated scope-schedule-cost plan. Compare project work against project execution to measure and manage performance.
1.3 | PROJECT MONITORING ARTIFACTS | The Project Monitoring artifacts contain documents required to track, review, and regulate the progress and performance of the project; identify any needed changes to plans, and initiate the changes. | All | Review and monitor performance against plan. | [7 empty] | Project performance is monitored regularly and consistently to identify variances from the Project Management Plan.
1.3.1 | Performance Reports | Status reports that accurately describe project progress against plan. | All | Collect project metrics. | Daria Adams | ePMO | Senior PM |  | Template |  |  | Data is accurate.
1.3.2 | Baseline Change Control Report | This report establishes a database of BCR's for managing Baseline change activity for each investment project. | All | A performance measurement of Baseline Changes is established for investment projects. | Daria Adams | ePMO | Senior PM |  | Template |  |  | Unauthorized changes to the baseline are not made. Baseline changes have been approved for any baseline changes. Baseline changes are not approved for significant variances. Baseline changes are infrequent and rare (no more than 3 in the past 2 years).
1.3.3 | Lessons Learned Reports | Lessons Learned Reports contained in the Lessons Learned Database from past projects have been reviewed during project planning. | All | Document project findings using the Lessons Learned Database. | Alex Howe | Enterprise Quality & Technical Change Management Group | Senior PM |  | Link to LLDB |  |  | All aspects of the project or project stage have been analyzed and results are documented. The results have been put into the Lessons Learned Database.
1.3.4 | Cost Estimate and Spend Report | A comparison of actual costs to the planned budget. This is a tool to monitor how the project is performing as noted in the Cost Management Plan. | All | Track actual costs against planned costs. | Daria Adams | ePMO | Senior PM |  |  |  |  | As identified in the Cost Management Plan.
1.3.5 | Risk Log | The Risk Log or Risk Register tracks all identified risks, triggers, and mitigation plans for the project. The risks should be reviewed on a regular basis and updated as needed. | All | Identify risks using a risk statement, assess risks to determine impact, plan risk responses, and monitor risks. The Risk Log is then used to assist the team in developing a risk adjusted schedule. | Daria Adams | ePMO | Senior PM |  | Template |  |  | Risk event statements should be specific and use complete sentences. The area of impact must be identified. Risks must be assessed to determine impact. High impact risks must have a risk response identified along with a risk owner.
1.3.6 | Project Schedule | The planned dates to start and complete tasks and milestones. Schedules should include work to be done by FSA as well as any vendors participating on the project. The schedule should be managed using the Schedule Management Plan. | All | Identify deliverables and milestones. Include any tasks required to monitor progress towards the deliverables and milestones. Conduct an integrated baseline review of the schedule to ensure all parties agree to the schedule. | Charlie Yi | ePMO | Senior PM |  | Template |  |  | All team members agree to the schedule. The schedule should be: duration driven with few constrained dates; resource loaded, and have dependencies identified.
1.3.7 | Action and Issue Log | The Action and Issue Log tracks action items, issues (risks when the trigger date is within 30 days of occurring), status, and resolution. | All | Identify action items and issues, assign owner, and monitor progress. | Daria Adams | ePMO | Senior PM |  | Template |  |  | An owner and status is noted for each item in the log. Resolutions are recorded as appropriate.
1.4 | MANAGEMENT STAGE GATE 1: INVESTMENT REVIEW BRIEFING | The Initiative Vision and High Level Requirements artifacts are reviewed and the project is approved or rejected at this time. Receiving approval to proceed to the Definition stage signals successful completion of this Stage Gate. | Vision | The Project Steering Committee will meet with the IPT and review the process inputs/artifacts created during the Initiative Vision stage to assess whether or not the proposed initiative warrants further effort and funding. The Steering Committee then makes a recommendation to the IRB. | Daria Adams | ePMO/TO | Senior PM |  | Template |  |  | Assigned recommendation from the Project Steering Committee to the IRB and a formal decision memo assigned by the Chair of the IRB.
1.5 | MANAGEMENT STAGE GATE 2: REQUIREMENTS REVIEW BRIEFING | To determine that project requirements are accepted by the business sponsor and by the Technology Office as sufficient for entry into the development stage. This stage gate review also requires validation that project deliverables have been accepted and that the project is being managed effectively. | Definition | The Project Steering Committee meets with the IPT and reviews the process inputs/artifacts to assess whether or not the proposed initiative warrants further effort and funding. | Daria Adams | ePMO/TO | Bus PM |  | Template |  |  | The business sponsor indicates business needs are accurately represented by requirements. The Technology Office representative indicates that requirements are technically adequate to support development activities. The Contracting Officer indicates the project contract deliverables have been accepted.
1.6 | MANAGEMENT STAGE GATE 3: PROJECT CLOSEOUT REVIEW BRIEFING | This stage gate ensures that the system is functioning properly post implementation, that the system is ready to proceed from implementation to operations and maintenance stage, as well as to document final lessons learned and perform project closeout. | Implementation | Prepare report of actual against plan. Document any outstanding issues or actions and who has ownership responsibility post-project. Ensure all project deliverables are included in organizational repositories. | Daria Adams | ePMO | Senior PM |  | Template |  |  | The sponsor accepts the closure of the project and the Project Closure Report.
2 | ACQUISITION
2.1 | ACQUISITION STRATEGY | The Acquisition Strategy is tailored to the particular project requirements. The Strategy is the program manager’s overall plan for satisfying the project need. It describes the project acquisition needs in details in include; analysis of alternatives, risk management plan, modular contracting vs. multi-step acquisition considerations, full and open competition vs. small business set aside, firm fixed price contract or time and materials, services procured independently or through GSA, etc. The plan describes all (including all non-Federal) contracts and/or task orders currently in place or planned for the project. In addition, the Strategy is an input for OMB 300, Section C: Acquisition/Contract Strategy. The strategy should be developed in accordance with FAR 34.004 and 7.105. (FAR Part 34 Implements OMB A-109-- Major System Acquisition) The Strategy should discuss in detail: (1) interoperability of contractor deliverables for the project; and (2) the project management plan (evaluation) requirements for contractors that may work on contracts supporting this project. The Strategy evolves through an iterative process and becomes increasingly more definitive in describing the essential elements of the program. Additionally, the Strategy serves as baseline to identify future acquisition plan requirements under this project. | Vision | Develop a tailored Acquisition Strategy for the needs of the program IAW FAR 34.004 and 7.105. | Dega Hussen | Acquisitions | Senior PM |  |  |  |  | Tailored Acquisition Strategy is prepared in writing IAW FAR 34.004 and 7.105.
2.2 | PRE-AWARD ARTIFACTS
2.2.1 | Statement of Need | The Statement of Need identifies the current organizational problem or inefficiency, affected stakeholders, and provides a high-level explanation as to how the project in question will benefit the agency. The document must address the business requirements in relation to the Acquisition Strategy. | Vision | Define the problem, its causes and symptoms. Gather data to support the existence of the problem and extent of your need. Decide the expected outcome of the procurement. | Dega Hussen | Acquisitions | Senior PM |  |  |  |  | Business need corresponds with the Acquisition Strategy.
2.2.2 | Market Research Report | Market Research is the process of collecting and analyzing information about the entire market available to meet the agency’s statement of need. This is to maximize reliance on the commercial marketplace and to benefit from its capabilities, technologies, and competitive forces in meeting an agency need. (FAR Part 10). | Vision | Adherence to the Market Research procedures/guidance found in FAR 10.002 (b). These procedures further the agency's understanding of the available solutions to an identified need. These can include issuing RFIs, exploring COTS options, learning about industry best practices, technology trends, etc. (See FAR 10.002(b) for further details/guidance). | Dega Hussen | Acquisitions | Senior PM |  |  |  |  | The documented findings from performed market research activities including alternatives analysis, costing, technology-specific risk analysis and an examination of private sector best-practices related to the goods/services being delivered. This may include the identification of potential supplier sources from searching government-wide acquisition contracts such as GSA Schedules.
2.2.3 | Acquisition Plan | The Acquisition Plan addresses all technical, business, management, and other significant considerations that will control an acquisition. It summarizes the planning considerations and identifies milestones in the acquisition process. Specific requirements can be found in the FAR section 7.105. The Acquisition Plan is to be developed collaboratively by the acquisitions team members including program manager, Contracting Officer’s Representative, and Contracting Officer. | Definition | Prepare written Acquisition Plan IAW FAR 7.105. | Dega Hussen | Acquisitions | Contracting Officer and Senior PM |  |  |  |  | The plan adequately addresses all content requirements identified in FAR 7.105 . The acquisitions budget is feasible and realistic. The Acquisition Plan also mitigates project risks. The Acquisition Plan corresponds to the identified project requirements outlined in the Acquisition Strategy (e.g. develop evaluation factors to evaluate the vendor's proposed project management plan against government's project management plans etc.).
2.2.4 | Statement of Objectives or Performance Work Statement | This document identifies the objectives to be meet by the acquisition by describing and setting forth the scope of work to be performed by the selected contractor. Additionally, a detailed independent government cost estimate (IGCE) is the agency’s estimate of the resources and the associate cost of these resources that a prudent business will incur in the performance of a contract. It is used to determine if adequate funding is available to perform the job; determine appropriate funding approval levels; inform the acquisition plan and the procurement method, and approval levels for the acquisition. | Definition | Identify and document the scope and associated tasks of the project that will need vendor support. Prepare IGCE based off of research of the requirement. Obtain purchase request. Identify any deliverable interoperability requirements, and LMM deliverable requirements to be included in the contract. | Dega Hussen | Acquisitions | Senior PM |  |  |  |  | The work statement is reflective of the statement of need. The work statement clearly and accurately documents the objectives to be achieved, deliverables to be produced and explains the activities to be performed in support of the project. Additionally, include an independent government cost estimate (IGCE) and purchase request in the work statement artifacts.
2.2.5 | Source Selection Plan | Formulated by the acquisition team, the Source Selection Plan specifies key elements of a proposed acquisition by identifying milestones against which a decision will be made. The plan should address all technical, business management, and other significant considerations that will control the procurement. Develop evaluation factors to evaluate the vendor's proposed project management plans against government's project management plans. The specific content of plans can vary, depending on the nature, circumstances, and state of the acquisition (FAR 7.105). Utilize the same evaluation factors identified in the acquisition plan. | Definition | Determine evaluation objective criteria. Establish an evaluation team. Identify the need for any advisory boards or panels. | Dega Hussen | Acquisitions | Program Manager/IPT |  |  |  |  | Evaluation team is identified and clearly understands the evaluation criteria. Advisory boards identified. All proposals are evaluated based solely on the factors and sub factors contained in the solicitation. Evaluation factors are aligned with the requirements identified in the Acquisition Strategy.
2.2.6 | Solicitation | The solicitation is the formal document issued to vendors describing the services/goods requested by the agency. The Solicitation will feature the work statement, key procurement contacts (CO, COTR) as well as details regarding the contract to be awarded. Specific requirements can be found in the FAR section 2.101. (Solicitations under sealed bid procedures are called “invitations for bids.” Solicitations under negotiated procedures are called “requests for proposals.” Solicitations under simplified acquisition procedures may require submission of either a quotation or an offer. NOTE: in accordance to agency's policy, solicitations may need to be presented to Contract Review Board for review and recommendation.) | Definition | Work with Contracting Officer(s) to write and publish the formal solicitation via the appropriate channels (e.g. FBO). Technical review of proposals and negotiation. | Dega Hussen | Acquisitions | Contracting Officer |  |  |  |  | The solicitation features the statement of work, key dates (proposal due date, period of performance), key contract personnel, etc. in accordance with relevant parts of the FAR.
2.3 | POST-AWARD ARTIFACTS
2.3.1 | Contract | Contract is a mutually binding legal relationship in which the contractor is obligated to furnish the required supplies or services and the agency is required to pay for these supplies or services. It includes all types of commitments that obligate the Government to an expenditure of appropriated funds and that, except as otherwise authorized, are in writing. Contracts do not include grants and cooperative agreements covered by 31 U.S.C. 6301, et seq. See FAR 2.101. | Definition | Ensure legality of contract and its compliance with the Federal Acquisition Regulation System. Obtain all necessary authorization and signatures. | Dega Hussen | Acquisitions | Contracting Officer |  |  |  |  | The contract is consistent with meeting the government's business needs as defined in the solicitation as well as relevant regulations, guidance, standards, processes, and procedures.
2.3.2 | Performance Monitoring Plan | The Performance Monitoring Plan describes all dealings between the agency or agencies and the contractor; from the time the contract is awarded until the work has been completed and accepted or the contract terminated, payment has been made, and disputes have been resolved. It should contain clear measurements of the contractor’s performance against the stated objectives. A quality Assurance Surveillance Plan or Contract Monitoring Plan are types of Performance Monitoring Plan. The day-to-day administrative monitoring such as invoice inspection and acceptance, timely review of submitted deliverables, and other activities may be documented in a COR work plan separate from this plan. Prepares Contractor Past Performance Assessments (CPAR). (NOTE: contracts with a value exceeding $150,000 are required to have an associated monitoring plan in which the agency outlines a process for managing, modifying, and closing out a contract. The CORs are required to keep/maintain all performance related documentation i.e., deliverable acceptance, key emails/correspondence with the vendor etc.) | Development | Determine the required level of contract surveillance. Determine what contract administration functions (if any) will be delegated and who they will be delegated to. Ensure that any functions delegated to the COR are not re-delegated to anyone. | Dega Hussen | Acquisitions | Contracting Officer/COTR |  |  |  |  | The Performance Monitoring Plan is comprehensive in its assignment of roles and functions for contract overight. The plan ensures that contractor performance will be closely monitored and that administering personnel will be quickly able to identify and take appropriate action if contract performance becomes unsatisfactory. See ACS Directive 2108. See the revised FSA COR/Contract Monitoring and Contract Records Policy.
3 | SECURITY AND PRIVACY
3.1 | INFORMATION SYSTEM SECURITY OFFICER APPOINTMENT LETTER | A three paged memorandum officially appointing an Information System Security Officer to the system in question. ALL systems must have an ISSO assigned to them, and this assignment is done via the ISSO appointment letter. This letter must be updated to reflect personnel changes. The letter must be signed in the "Definition" stage. | Definition | The System Manager or Project Manager officially assigns an Information System Security Officer using the ISSO Appointment Letter. Both the System Manager and the ISSO assigns the responsibility sections for the appointment. | Kimberly Barks | IT Risk Management | Bus PM |  | Template |  |  | ISSO Appointment Letter must officially appoint an Information System Security Officer to the system in question.
3.2 | PRIVACY ARTIFACTS
3.2.1 | Privacy Threshold Analysis | The Privacy Threshold Analysis is used to determine whether a Privacy Impact Analysis is necessary. The PTA determines all subsequent privacy requirements (eg, Privacy Impact Assessment, System of Records Notice, Computer Matching Agreement), and should be completed in the "Definition" stage. | Vision | Determine whether or not the system will handle personally identifiable information. Once this determination has been made, determine how this information will be collected, used and secured. | Chuck Tobler | IT Risk Management Group | Bus PM |  | Template |  |  | The document must comply with the standards set forth in the E-Government Act. The standard FSA PTA template must be used. Fields must contain the same data collected from the from the FSA PTA artifact and support the analysis necessary to perform the Privacy Impact Analysis.
3.2.2 | Privacy Impact Assessment | The Privacy Impact Assessment is used to identify if a system contains privacy information and lets the public know what information is collected and how it is secured. Information collected may include Social Security Numbers, PINs, Addresses, Dates of Birth, etc. The PTA (above) determines whether a PIA is required. PIAs often require multiple levels of approvals/signatures (including ED OM Privacy), and should be completed as soon as possible due to the length of time required for necessary approvals. A system cannot go live until the PIA is reported to the Office of Management and Budget and posted to the OM Privacy website. | Vision | If the system processes or contains personally identifiable information, a Privacy Impact Assessment must be completed and assigned by program officials. | Chuck Tobler | IT Risk Management Group | Bus PM |  | Template |  |  | The artifact must provide information that details whether the system contains privacy information, how the data is collected and secured. The standard FSA PIA template must be used, and all questions must be sufficiently answered. The PIA must be signed by the program officials. If the system uses Social Security numbers, the PIA must be assigned by the COO.
3.2.3 | System of Records Notice (SORN) | Describes the Privacy Act system of records, and the categories of PII collected, maintained, retrieved, and used within the system. It provides information to the public on various characteristics of the system (e.g. description, purpose, data collection, notification, retention and disposal, etc.) The template is located at the end of the directive on Privacy Act issuances. The PTA will help determine if a SORN is required; however, it is best to check with the FSA Privacy Advocate during the "Vision" stage. The SORN process can take up to 8 months and requires many levels of approval, including letters to Congress. Further, the SORN must be posted for public comment in the Federal Register 40 days before the system goes live. | Definition | Determine whether or not the system will handle personally identifiable information and Privacy Act information. Consult with the FSA privacy advocate to see if a System of Records Notice (SORN) is required. If a SORN is required, the SORN must be written and published in the Federal Register. | Chuck Tobler | IT Risk Management Group | Bus PM |  | See guidance, p.358 |  |  | The SORN describes the categories of PII collected, maintained, retrieved and used within the system. The standard SORN template must be used, and all questions must be answered. The SORN must go through multiple reviews, including the FSA Privacy Advocate, PLI, OGC, and DRS.
3.3 | EXTERNAL DATA EXCHANGE ARTIFACTS
3.3.1 | Memorandum of Understanding | Defines the responsibilities of distinct organizations/units in securing the interconnection between connected systems including the Interconnection Service Agreement (ISA). The MOU process can be lengthy, and requires multiple levels of approval. Discussions about MOUs should be started during the "Vision" stage. | Definition | If the system is connecting with an external system, a memorandum of understanding must be written and assigned by program officials from each agency/organization. | Chuck Tobler | IT Risk Management | Bus PM |  | See Guidance |  |  | The Memorandum of Understanding (MOU) must define the responsibilities of distinct organizations in securing interconnection between connected systems. This must include the Interconnection Service Agreement.
3.3.2 | Computer Matching Agreement | A computer matching agreement is a written document that establishes the conditions, safeguards, and procedures under which one government entity agrees to disclose data to another entity, where there is to be a computerized comparison of two or more automated System of Records (SORs). It is a specific requirement of the Privacy Act of 1974. If one agency exchanges Privacy Act data (ie, PII) with another Federal agency to determine if someone is eligible for a Federal benefit, then a CMA is required (even if there is already an memorandum of understanding and interconnection security agreement in place). The CMA process can be lengthy, and requires multiple levels of approval. Discussions about CMAs should be started during the "Vision" stage. | Development | If a system is exchanging Privacy Act-protected information with another Federal Agency to determine eligibility for benefits, then a Computer Matching Agreement must be written and assigned by senior agency officials. | Chuck Tobler | IT Risk Management | Bus PM |  | See Guidance |  |  | The Computer Matching Agreement must establish the conditions, safeguards and procedures that define how the government entity discloses data to another entity when there is a computerized comparison of two or more system of records. The agreement must go through multiple reviews, including the FSA Privacy Advocate, PLI, OGC, and DRS. The agreement must be approved by the Data Integrity Board.
3.3.3 | Interconnection Security Agreement (ISA) | Required for Inter-agency Agreements (IAAs) involving the interconnection of two systems owned by two different agencies. The ISA provides the technical solution and security requirements for the interconnection. The ISA also supports a Memorandum of Understanding or Agreement (MOU/A) between organizations. The ISA process can be lengthy, and requires multiple levels of approval. Discussions about ISAs should be started during the "Vision" stage. | Development | If the system is connecting (sharing data) with an external system, an interconnecting security agreement must be written and assigned by program officials from each agency/organization. | Chuck Tobler | IT Risk Management | Bus PM |  | Template (ISA) Creation Checklist Validation Checklist |  |  | Establishes individual and organizational security responsibilities for the protection and handling of unclassified information between two organizations. Any specific requirements of both signatory organizations are also included.
3.4 | CONTINUITY OF SERVICES ARTIFACTS | These artifacts are to ensure that critical business functions supported by a system continue to operate in the event of an emergency or disaster. The documents included in these artifact detail roles and responsibilities in the event of a system outage, system vulnerabilities, risk mitigation strategies as well as prevention planning assigned to minimize the likeliness of a system outage/failure. | Implementation | Develop Standard Operating Procedures in case of system outage. Assign roles and responsibilities in case of a system outage. Determine how the system will be recovered and if there will be an alternate, secondary location warehousing system infrastructure. | [7 empty] | The documents developed for Continuity of Services demonstrate a clear and effective plan for ensuring system stability in the event of an outage.
3.4.1 | Business Impact Analysis (BIA) | This is an application level document that reveals any vulnerabilities, and a planning component to develop strategies for minimizing risks. Often part of the disaster recovery plan, it is likely to identify costs linked to failures, such as loss of cash flow, replacement of equipment, salaries paid to catch up with a backlog of work, and loss of profits. | Implementation | Retrieve the BIA and Appendix A templates and complete the templates in their entirety. Obtain the necessary signatures. Upload the completed document on OVMS (only system/application specific ISSO/SSO will have access. | Chuck Parrill | Infrastructure Operations Group | IT PM |  | Template |  |  | The BIA must define all potential system vulnerabilities and related cost impacts, as well as describe the strategies for minimizing vulnerabilities and risks.
3.4.2 | Information Technology (IT) Contingency Plan (Includes Test Plan) | Documents the critical business functions that need to be resumed and in what order, what technical components are affected in the case of a disaster, and the key individuals who should be familiar with their duties under the plan. The same template may be used for both the Contingency Test Plan and Disaster Recovery Plan, depending upon need. | Implementation | Access the template and complete it in its entirety. Obtain the appropriate signatures. Upload the completed document on OVMS (only system/application specific ISSO/SSO will have access). | Chuck Parrill | Infrastructure Operations Group | IT PM |  | Template |  |  | The plan must include procedures and technical measures that enable the recovery of IT systems, operations, and data after a disruption. Contingency planning generally includes one or more of the approaches to restore disrupted IT services: •Restoring IT operations at an alternate location •Recovering IT operations using alternate equipment •Performing some or all of the affected business processes using non-IT (manual) means (typically acceptable for only short-term disruptions).
3.4.3 | Contingency Test Plan Results | Test Plan Results are not at the application level. Test Plan Results are only required if not already covered by an existing enterprise level Contingency Plan Test Results document. | Implementation | Access the template and complete it in its entirety after an Exercise. Obtain the appropriate signatures. Upload the completed document on OVMS (only system/application specific ISSO/SSO will have access). | Chuck Parrill | Infrastructure Operations Group | IT PM |  | Template |  |  | Test Plan Results must document results of conducting the predefined Contingency Test Plan.
3.4.4 | Disaster Recovery Plan | This is a standard operating procedure that describes how at an enterprise level the organization is to deal with potential disasters by explaining the precautions taken so that the effects of a disaster will be minimized and the organization will be able to either maintain or quickly resume mission-critical functions. Disaster Recovery Exercise reports quality management findings and human capital results at the enterprise level. This artifact is required unless already covered by an existing enterprise level Disaster Recovery Plan prepared by the vendor responsible for management of the VDC contract. The same template may be used for both the Contingency Test Plan and Disaster Recovery Plan, depending upon need. | Implementation | This contains VDC restoration activities that are compiled into one document versus application specific. | Chuck Parrill | Infrastructure Operations Group | IT PM |  | Template |  |  | The Disaster Recovery Plan must describe how the organization will deal with a potential disaster by defining vulnerabilities and precautions taken to mitigate or quickly resume mission critical functions. The plan must define how to execute the Disaster Recovery Plan and what data is expected from quality management and human capital reporting post exercise.
3.5 | SYSTEM SECURITY DOCUMENTATION ARTIFACTS | These artifacts are comprised of system security documents that define security related roles and responsibilities, provide an overview of systems, categorize personally identifiable information, and also detail system security requirements, known security weaknesses, and controls in place to protect the security of the system. |  | The System Security Documentation Package is comprised of documents that support the implementation of security controls and continued operation of a system. It is the responsibility of the ISSO and system manager to ensure these documents are completed either through contract or using in-house resources. | [7 empty] | Provides comprehensive insight into how system security will be managed. All fields have been completed and checked for quality and accuracy to ensure all security documentation complies with NISST SP 800-18 and SP 800-53.
3.5.1 | Data Sensitivity Worksheet | The Data Sensitivity Worksheet is used to assess the security and sensitivity of a system. It is used to classify a system as either a general support system (GSS) or a major application (MA), identify data sensitivities, and to ensure that the system has the appropriate level of security. Because the data sensitivity worksheet, to a large extent, will determine the security control requirements (eg, if a full security authorization is required), for new systems, it must be completed during the "Vision" stage. For upgrades/enhancement releases, the worksheet must be reviewed and updated accordingly. | Vision | The ISSO will ensure that it is appropriately filled out to identify the correct data sensitivities. These data sensitivities will be used to identify the appropriate controls to be implemented for the security of the system. The data sensitivities identified here will be used along with NIST SP800-53 to develop the System Security Plan and the Security Assessment Plan. | Chuck Tobler | IT Risk Management Group | Bus PM |  | Template |  |  | The artifact must be able to assess the security and sensitivity of a system. It should be able to classify the system as either a GSS or MA, identify any data sensitivities, and document support that the system has the appropriate level of security.
3.5.2 | System Boundary Template (System Authorization Boundary) | Artifact developed during the definition phase if constructing a new system or application or updating an existing system. Defines system boundaries for and relationships between systems and communication channels. If an artifact is necessary, a Memorandum of Understanding (MOU) specific to the boundary document must be prepared. For new systems, the boundary template must be completed during the "Vision" stage. For upgrades/enhancement releases, the boundary template must be reviewed and updated accordingly. | Definition | Define the system boundary and the relationship between the system and other systems where relevant. Provide an overview of the security requirements for the system and methods by which the system will be secured. Define the upfront system actions and performance. | Theon Dam | IT Risk Management Group | Bus PM |  | Template |  |  | The System Boundary Template must define the system boundaries for and relationship between different systems and communication channels.
3.5.3 | System Security Plan | Provides an overview of the security requirements of the system and describe the controls in place or planned, responsibilities and expected behavior of all individuals who access the system. The System Security Plan should be viewed as documentation of the structured process of planning adequate, cost-effective security protection for a system. Describes general system information such as its Federal Information Processing Standards (FIPS) 199 categorization, type of data processed, points of contact, system environment, applicable Federal laws and guidelines, and sensitivity of information processed by the system. It includes the management, operational, and technical controls required for the system. System Boundary Document and all other project related security documentation must be developed in compliance with NIST Special Publication (SP) 800-18 and SP 800-53. Further security compliance information can be found at: http://csrc.nist.gov/publications/PubsSPs.html. As deemed necessary, contractors may obtain a copy of the Federal Student Aid Security Architecture Model and other security documentation by contacting their Contracting Officer post award. Different versions are available based on need. For new systems, the system security plan is generally completed during the "Definition/Development" stages. For upgrades/enhancement releases, the plan must be reviewed and updated accordingly. | Definition | The System Security Plan (SSP) is either created by a contractor or by in-house resources. The ISSO is responsible to ensure it is created based on the data sensitivities, system boundaries, and controls identified for implementation. It is first drafted in the Definition phase and authorized for use prior to a system moving into production. The SSP is a living document and will be updated throughout the system's lifecycle. The SSP will be reviewed at least annually. | Chuck Tobler | IT Risk Management Group | Bus ISSO, TO, CISO |  | Template |  |  | The System Security Plan must provide system security requirements and describe the management, operational and technical controls in place as well as responsibilities and expected behavior of those accessing the system. It should describe general system information mapping to FIPS 199 categorization, the type of data processed, points of contact, system environment, applicable federal laws and guidelines and any sensitive information processed by the system. The System Security Plan will be approved by the FSA CISO.
3.6 | SECURITY RISK ASSESSMENT ARTIFACTS | The Security Risk Assessment artifacts provide an assessment of a system’s security controls and determines the extent to which those controls have been implemented correctly - operating as intended and producing the desired outcome with respect to meeting system security requirements and a plan to mitigate findings. The security assessment also includes a list of any recommended corrective actions. The guidance is used to create the artifacts. |  | Work with FSA security personnel to perform a thorough assessment/analysis of the system's security. | [7 empty] | The security assessments and respective reports are thorough and actionable.
3.6.1 | Security Assessment Plan | The system's Security Assessment Plan is a document that identifies all the security controls that will be assessed and the assessment methods used for a System Security Authorization Assessment. The security assessment plan must be completed before any security assessment activities may take place. | Development | Using the System Security Plan and the System Boundary Template, the Independent Assessor for the system controls will create a Security Assessment Plan. The Security Assessment Plan will be approved by the ISSO and the FSA Compliance Manager. | Chuck Tobler | IT Risk Management Group | Bus ISSO, TO Compliance Manager |  | N/A |  |  | The System Security Assessment Plan will be reviewed to ensure it includes the appropriate controls and control levels for a system based on the System Security Plan. If approved, it will be assigned by the ISSO and FSA Compliance Manager.
3.6.2 | System Security Documentation Checklists | These checklists are to be compared against security plans. For new systems, this step is completed in parallel with development activities. For existing systems, this step must be completed either every 3 years, or whenever there is a major change to the system. | Development | For the initial security authorization of the system, the ISSO will use this checklist to ensure the system's security documents are ready for review by an independent assessor. The ISSO will then provide the Independent Assessor the checklists to be completed by the Assessor for the security documentation. The assessor will provide the completed form back to the ISSO to include within the Security Authorization Package. The ISSO will continue to use the checklist for periodic internal reviews throughout the system's lifecycle. | Chuck Tobler | IT Risk Management | Bus ISSO |  | Template |  |  | Used to evaluate the completeness of the security plans.
3.6.3 | Security Assessment Report | Report defines accreditation boundary, system characteristics, and Risk Assessment Results. For new systems, this step is completed in parallel with development activities. For existing systems, this step must be completed either every 3 years, or whenever there is a major change to the system. | Development | An Independent Assessor will complete a security assessment of the system based on the Security Assessment Plan. The Independent Assessor will then document their findings within the Security Assessment Report and submit the report to the ISSO. | Chuck Tobler | IT Risk Management | Bus PM |  | Template |  |  | The Security Assessment Report must define the accreditation boundary, system characteristics, and the Risk Assessment Results.
3.6.4 | Plans of Actions and Milestones (POAMs) | The Plan of Actions and Milestones Report addresses and tracks all weaknesses identified by audits, assessments, reviews and evaluations. The POA&M Report must be completed before a system may receive and authority to operate, and after any type of security assessment, such as a Production Readiness Review or a monthly authenticated scan. POA&Ms must be updated periodically, but at least quarterly. | O&M | Deficiencies identified against a system will be documented in a Plan of Actions and Milestones. The ISSO will ensure mitigation strategies are identified for security deficiencies identified in the Security Assessment Report. The ISSO will also ensure that all security deficiencies, from any source, that are identified throughout the system's lifecycle are documented as POAMs. | Vacant | IT Risk Management | Bus ISSO, TO Compliance Manager |  | Template |  |  | The POAMs must address and track all weaknesses identified by audits, assessments, reviews and evaluations.
3.6.5 | This Artifact has been Removed.
3.7 | AUTHORITY TO OPERATE LETTER & BRIEFING | The Authority to Operate Letter and Briefing proves the system has gone through system accreditation and certification. The briefing is a presentation to the authorizing official, providing an overview of the security authorization and risk. An independent contractor creates this Power Point presentation. For new systems, these must be completed before a system is implemented in production. For existing systems, these must be completed every three years or whenever a system undergoes a major change. | Testing | This letter is created after an independent security assessment for a system is completed. The assessment's identified risks are noted in a briefing presented to the Business Owner and Security Authorization Official. The Authority to Operate Letter is presented to the Security Authorization Official for signature. The Authorizing Official will sign the letter and approve the system's operation if the risks posed by its operations are found acceptable. | Theon Dam | IT Risk Management | Bus ISSO, TO CISO, CIO |  | N/A |  |  | The Authority to Operate Letter and Briefing prove the system has gone through system accreditation and certification and provide a comprehensive overview of the security authorization and risk. Documentation collected must be comparable to the System Security Plan, Configuration Management Plan, IT Contingency Plan, System Security Documentation Checklist, Security Assessment Plan, Plans of Actions and Milestones, and the Security Assessment Report.
3.8 | This Artifact has been Removed. | [7 empty] | Template
3.9 | DATA RETENTION SCHEDULE | The Data Retention Schedule details the length of time and manner in which information must be retained. | Vision | Work with FSA Records Liaison Officer(s), Business Unit Records Management Officer (BURMO), and the Records Management Team at the Office of Management's Privacy, Information and Records Management Services (PIRMS) to develop a record schedule and have it approved by the National Archives and Records Administration (NARA). | Christine Wyatt | Information and Record Management Group | Bus PM |  | Template |  |  | Artifact must define document retention requirements including timing, format and detail retained. Until there is a retention schedule for these records all records will be treated as unscheduled records. Unscheduled records are retained as permanent records (kept forever) until they are scheduled.
4 | REQUIREMENTS
4.1 | INITIATIVE VISION DOCUMENT | This document describes stakeholder needs and business problems to be addressed by the features or capabilities of the new initiative. The document also describes high-level business processes, and system context of the envisioned solution. Document forms the initial basis for requirements traceability in later stages. Tailoring Guidance: For small projects, or subprojects (projects under the umbrella of an overall program), the Initiative Vision Document may not be required, providing that either the Project Charter, Investment Request or overarching (program) Initiative Vision Document addresses the requisite information. | Vision | Collect, analyze, and define high-level needs and features of the system. Determine capabilities needed by the stakeholders and the target users, and why these needs exist. Establish Business Vision and Stakeholder wants and Needs. Develop conceptual initiative-specific target state, in narrative and graphical format. Describe the business opportunity and problem being solved by the initiative. Describe product features, overview, and compare to other existing documents. Define assumptions and dependences. | Caryn Boyd | Application Development Group | Bus PM |  | Template |  |  | Target state, system needs and requirements, vision, and overall product features are accepted by the project sponsor. Business opportunity is addressed and proposed system addresses defined problem.
4.2 | REQUIREMENTS MANAGEMENT PLAN | The purpose of the Requirements Management Plan is to define the requirements processes and procedures to be used by the project team. This Plan defines how requirements will be elicited, structured and prioritized; how requirements will be recorded; how requirements will be modified; and how requirements will be traced and reconciled for final delivery of the product. The plan also specifies roles and responsibilities. Tailoring Guidance: A Requirements Management Plan is generally required. For small in-house projects where overall project risks are low, requirements management controls may be addressed directly in the Project Management Plan, the Change Management Plan and the Configuration Management Plan. The project team must demonstrate that the requisite subjects have been addressed (consult with designated LMM subject matter expert). | Vision | Develop/assign roles and responsibilities relating to requirements management. Develop a categorization for requirement types and requirement attributes. Develop a system for requirements traceability and requirements reporting. | Caryn Boyd | Application Development Group | Bus PM |  | Template |  |  | The Requirements Management Plan clearly assigns roles and responsibilities for requirements management throughout their lifecycle. The plan also clearly addresses how requirements will be managed as a configuration item, and what tools will be utilized to support any and all aspects of requirements management.
4.3 | HIGH LEVEL REQUIREMENTS DOCUMENT | This document captures high level functional and non-functional requirements in a format suitable for the project at hand. The document must address the breadth of coverage, and provide at least a preliminary description of how requirements may be grouped into releases and iterations. | Vision | Establish Scope of the target product. Develop high level use case and functional and non-functional requirements. Group and prioritize requirements. Identify preliminary options for transitioning from current state to implementation of the requirements. | Caryn Boyd | Application Development Group | Bus PM |  | Template |  |  | Functional and non-functional requirements are traceable to customer wants and needs in the Initiative Vision Document. Requirements are clearly articulated and testable. Requirements, and their grouping and prioritization, are sufficient to plan further elaboration, and are accepted by the project sponsor.
4.4 | USER INTERFACE (UI) SPECIFICATION DOCUMENT | The User Interface Specification Document provides the details of the software user interface - covering all possible actions that a user may perform and all visual, auditory and other interaction elements. | Definition | Define user interface specification, requirements and information flow. Develop wire frames and navigational constructs. | Patrick Fedorowicz | Enterprise IT Architecture and Strategic Infrastructure Group | IT PM |  | Template |  |  | Detailed UI for all applicable components in the requirements are addressed. Document should identify all interactions. Project sponsor accepts deliverable.
4.5 | DETAILED REQUIREMENTS DOCUMENT | The Detailed Requirements Document captures detailed functional and non-functional requirements in the form of declarative statements, uses cases and other requirement artifact types as applicable to the project. Requirements in this document are captured at the level from which they can inform dedign and development. | Definition | Define and develop system context diagram and detailed use cases. Describe interfaces with external systems. Define the detailed system level requirements for the solution. Detail detailed functional and non-functional requirements for the solution. Define system constraints to provide the IT standards and other constraints applicable to the solution. Define the various business rules and messages required of the solution. Provide the logical data model. | Caryn Boyd | Application Development Group | Bus PM |  | Template |  |  | Use cases and requirements are clear and understandable. Project sponsor accepts use cases, all functional and non-functional requirements, and business rules and messages for the system.
4.6 | REQUIREMENTS TRACEABILITY MATRIX | The Requirements Traceability Matrix (RTM) ensures bi-directional traceability between high level/business and detailed/system requirements. The RTM also associates detailed/system requirements with portions of the build designed to satisfy them. Testing is also tied to the requirements on which they are based to ensure that the build meets all requirements. | Development | Document system requirements and how the system will meet these requirements. | Karen Edwards | Application Development Group | IT PM |  | Template |  |  | The requirements are thoroughly documented and compartmentalized in a way that facilitates system testing. Each requirement is uniquely identifiable and reflects bidirectional traceability.
4.7 | DATA MIGRATION PLAN | Document defines the processes associated with completion of the data migration effort; which includes conversion strategies, data mapping (which are the detailed requirements), data clean up, and testing. | Definition | Develop/determine a conversion strategy, data migration details, data migration order, data migration exceptions, and data migration validations. | Rick Armwood | Enterprise Data Services Group | IT PM |  | Template |  |  | The data migration plan features a comprehensive migration strategy with a risk minimizing means of performing the migration.
4.8 | TECHNICAL STAGE GATE 3: REQUIREMENTS REVIEW BRIEFING | This stage gate may be repeated at key project points to obtain agreement from key stakeholders that the requirements management practices are sound and that detailed requirements are ready for use by the solution delivery teams, and are sufficient to move from definition to the design phase of the project. | Definition | Stage Gate SMEs assess IPT inputs, obtain clarification when necessary and document their conclusions. Assess risks associated with the state of product artifacts and overall project status. | Caryn Boyd | Application Development Group | IT PM |  | Template |  |  | IPT receives recommendation from Stage Gate governance body and approval as appropriate.
5 | DEVELOPMENT
5.1 | CONFIGURATION MANAGEMENT PLAN | The Configuration Management (CM) Plan provides an overview of the organization, activities, overall tasks, and objectives of CM for an initiative. It addresses: baseline work products, describes the mechanism to track and control changes/change requests, and the mechanism to establish and maintain baseline integrity. | Definition | Identify roles and responsibilities of all participants in the Configuration Management Plan. Define process to track hardware and software changes and deployment procedures. | Teresa Toliaferro | Enterprise Quality & Technical Change Management Group | IT PM |  | Template (Agile) Template (Agile Charter) Template (Traditional) |  |  | Ensure all interfacing systems are taken into consideration. Ensure the plan doesn't conflict with existing CM's of other interfacing systems.
5.2 | PRELIMINARY DEIMGN DOCUMENT | The Preliminary Design Document provides a high level design, using a number of different architectural views (to include use case diagrams) to depict different aspects of a system. It is intended to capture and convey the significant architectural decisions that have been made on the system in the early stages, allowing the high-level design to be effectively evaluated before proceeding to the detailed design stage. | Development | Document logical design and logical data model. Identify and document design decisions. | Patrick Fedorowicz | Enterprise IT Architecture and Strategic Infrastructure Group | IT PM |  | Template |  |  | Design addresses all the functional and non functional requirements. Design addresses impact on other systems.
5.3 | DETAILED DEIMGN DOCUMENT | The Detailed Design Document provides a detailed design, using a number of different architectural views (to include use case diagrams) to depict different aspects of the system. It is intended to capture and convey the detail necessary to allow coders to develop the system, and to support critical design reviews before beginning development. | Development | Document physical design and physical data model. Document possible system interfaces. | Patrick Fedorowicz | Enterprise IT Architecture and Strategic Infrastructure Group | IT PM |  | Template |  |  | Design is consistent with requirements, Preliminary Design and Technology Standards. Proposed design is feasible and workable.
5.4 | SOLUTION SOURCE CODE AND DEPLOYABLE PACKAGES | Solution Source Code is a collection of statements or declarations written in a human-readable computer programming language. | Development | Package the deployable code. Define prerequisites for deployment. | Teresa Toliaferro | Enterprise Quality & Technical Change Management Group | IT PM |  | N/A |  |  | Deployable environment both hardware and software are defined and source are provided. Dependencies are defined. Deployment procedures are unambiguously defined.
5.5 | SOLUTION USER MANUAL | The Solution User Manual describes in detail the user/system interaction facilities offered by the system, which allow the users to leverage the system functionality in support of their business processes. | Testing | Identify and define all user interfaces. Identify and define all roles. | Vacant | Application Development Group | IT PM |  | Template |  |  | Ensure all the user interfaces are addressed. Ensure information flow is sequential.
5.6 | RELEASE VERSION DESCRIPTION DOCUMENT | The Release Version Description Document is used to track and control versions of software and hardware being released to implementation, testing, or the final operational environment. | Testing | Identify list of changes to the software, hardware, and other plug-in software components that are included in this release. | Teresa Toliaferro | Enterprise Quality & Technical Change Management Group | IT PM |  | Template/Guidance |  |  | Ensure release aligns with technology standards. Ensure release is tested to have no known issues or defects.
5.7 | TECHNICAL STAGE GATES 1A AND 1B: ENGINEERING REVIEW BOARD (ERB) REVIEW BRIEFING | Technical Review Stage Gates 1A and 1B verify that a system's technical solutions are in compliance with FSA's technical, architectural and target state vision objectives and the project is ready to pass from technical design to build/construct/test in the development stage. | Development | Develop a Preliminary Design Document and User Interface Design Document for review. Prepare the Detailed Design Document for review by the ERB. | Patrick Fedorowicz | Enterprise IT Architecture and Strategic Infrastructure Group | IT PM |  | Template |  |  | ERB recommends project to move to Development stage.
5.8 | TECHNICAL STAGE GATE 2: TEST READINESS REVIEW BRIEFING | The Test Readiness Review artifacts provide management with an assessment of the readiness of the development maturity, test environment, test data, test processes, deliverables and other dependencies to ensure the system is ready to pass from build/construct to formal system testing and that known risks have been documented, accepted or mitigated. | Development | The Test Readiness Review Body will meet with the IPT and review the Test Readiness Review checklist to assess and verify whether or not development requirements, artifacts, inputs, and project requirements have been met and activities completed. | Karen Edwards | Application Development Group | IT PM |  | Template |  |  | IPT receives a signed decision memo outlining the decision to proceed or delay, along with TRR report and findings.
6 | TESTING
6.1 | MASTER TEST PLAN | Master Test Plan: Provides a central artifact to govern the planning, control and test management of the test effort. It defines the general approach that will be employed to test the solution and to evaluate the results of that testing, and is the top-level plan that will be used by managers to govern and direct detailed testing activities. Supplemental phase level test plans (System, User Acceptance, Performance, Inter-system, etc.) provide detailed strategy (covering scope, resources, and approach) for the phase of testing focusing on what is to be tested in the phase. Additionally, the Master Test Plan provides objectives for the security control assessment and procedures for testing each security control. | Definition | Master Test Plan-Document testing, provides details at a high level and overall test planning and test management for multiple phases of testing (one project or across multiple projects). Phase Level- Document testing provides phase specific details for System , User Acceptance, Performance, Inter-system, etc. test plans. | Karen Edwards | Application Development Group | IT PM |  | Template |  |  | Master Test Plan addresses all aspects of testing covering all functional, non functional requirements covering all phase level test plans.
6.2 | TEST SUITES | Test Suites outline a set of several test scenarios, test cases and test scripts for a component or system under test. | Definition | Identify and create test scenarios and map to requirements. Define associated test procedures and test scripts. | Karen Edwards | Application Development Group | IT PM |  | Template (New Systems) Template (Legacy Systems) |  |  | All test suites and test cases are mapped back to requirements.
6.3 | TEST REPORTS | The Test Reports provide a summary of the system test phase of the project. The reports include support materials pertaining to the software version; deviations from those areas that were agreed to in the System Test Plan. The reports give an overall assessment of the product that was tested, and provide an overall status of the incidents found during the system test activity. The test reports also include a summary of findings from business user acceptance testing. | Testing | Document test results. Identify issues that will have major impact on the success of the project. | [7 empty] | Reports address the results of testing, provides a summarization of the test effort and a final assessment.
6.3.1 | User Acceptance Test Summary Report | The User Acceptance Test Summary Report gives a summarization of the user acceptance test phase of the project. The report includes support materials pertaining to the software version, deviations from those areas that were agreed to in the User Acceptance Test Plan, gives an overall assessment of the product that was tested and gives an overall status of the incidents found during the user acceptance test. | Testing | Summarize the user acceptance criteria and document whether the system satisfies the acceptance criteria. Also document whether users, customers, and other authorized entities can accept the system. | Karen Edwards | Application Development Group | IT PM |  | Template |  |  | The User Acceptance Test Summary Report summarizes the user acceptance test phase of the project. It must provide an overall assessment of the product tested and status of incidents occurring during user acceptance testing.
6.3.2 | Test Summary Report | This report gives a summarization of the system test phase of the project. The report includes support materials pertaining to the software version, deviations from those areas that were agreed to in the System Test Plan, gives an overall assessment of the product that was tested, and provides an overall status of the incidents found during the system test activity. | Testing | Summarize test activities and results. Evaluate the corresponding test items against the determined exit criteria. | Karen Edwards | Application Development Group | IT PM |  | Template |  |  | The Test Summary Report must summarize the system test phase of the project and include support materials related to version, deviations from the agreed upon System Test Plan. It must perform an overall assessment of the product tested and status of incidents identified during system test activity.
6.3.3 | Defect Management Report | The Defect Management Report details the defects discovered during testing. Various reports are required for each phase of testing. | Testing | Report defects and related metrics. The reported metrics should include both successes and failures. This report will also be used for process improvement efforts to either minimize defects in the future or to identify defects earlier in the development process. | Karen Edwards | Application Development Group | IT PM |  | Template |  |  | The Defect Management Report must detail all defects discovered during testing.
7 | IMPLEMENTATION
7.1 | IMPLEMENTATION / TRANSITION MANAGEMENT PLAN ARTIFACTS | These documents describes the planned procedures for releasing a new system or system module to production and how the organization will shift from a legacy system to a new system. | Definition | Document planning, preparing items to be delivered, packaging, shipping, installation, training that must take place, and support plan. Describe the procedures for changing over usage from the replaced system (if any) to the new system. Procedures described must address: handover support arrangements, handover schedule, roles and responsibilities, training, stakeholder management, migration strategy, documentation turnover, acceptance, implementation and transition acceptance. Document a brief description of the functionality of the project as a whole and, for multi-release projects, the current project release. Document the objectives of the plan. List the transition related principles, constraints and assumptions. Describe the enterprise level transition strategy for this release of the project. Define current and future state, then perform a gap analysis to recognize and confirm gaps, deIMGn transition approaches/initiatives, identify major risks and issues, and develop risk mitigation strategies. Define dependencies, stakeholders, who is developing the solution, and roles and responsibilities post transition. Document staffing needs, training needs, and inventory assets and documents to be transitioned. Conduct a transition readiness assessment. | [7 empty] | All fields within the Implementation Plan and Transition Management Plans have been completed and checked for accuracy. The project sponsor has accepted the plans. System implementation is successful, with all resources completing assigned tasks as required/defined by the plan.
7.1.1 | Implementation Plan | This document describes the planned procedures for releasing a new system or system module to production. It lists deployment goals; critical success factors; deployment tasks (including post implementation testing); resources, and tools; task and resource dependencies; task responsibilities and timelines for completion; and significant risks and contingency plans. | Definition | The implementation plan must document planning, preparing items to be delivered, packaging, shipping, installation, training that must take place, and support plan. | Teresa Toliaferro | Enterprise Quality & Technical Change Management Group | IT PM/BusPM |  | Template |  |  | The Implementation Plan must document planning, preparing items to be delivered, packaging, shipping, installation, training that must take place, and support plan.
7.1.2 | Transition Management Plan | This document includes all aspects of how the organization will shift from a legacy system to a new system. This plan covers the responsibilities associated with maintenance and support to a new contractor from the development contractor. | Definition | It should document a brief description of the functionality of the project as a whole and, for multi-release projects, the current project release. It should also document the objectives of the plan and list the transition related principles, constraints and assumptions. The plan should describe the enterprise level transition strategy for this release of the project. It must define current and future state, then perform a gap analysis to recognize and confirm gaps, design transition approaches/initiatives, identify major risks and issues, and develop risk mitigation strategies. It defines dependencies, stakeholders, who is developing the solution, and roles and responsibilities post transition. Staffing needs, training needs, and inventory assets and documents to be transitioned must be documented. Conduct a transition readiness assessment. | Vacant | Enterprise Quality & Technical Change Management Group | IT PM/BusPM |  | Template |  |  | The Transition Management Plan should describe the procedures for changing over usage from the replaced system (if any) to the new system. Procedures described must address: handover support arrangements, handover schedule, roles and responsibilities, training, stakeholder management, migration strategy, documentation turnover, acceptance, implementation and transition acceptance.
7.2 | TRAINING PLAN | The Training Plan documents the approach to knowledge transfer and the training to be provided or arranged for end-users and support staff, including prerequisites, courses, course curricula, mode of delivery and attendees. | Development | Document the techniques and tools, training requirements, schedule, curriculum, and materials and equipment required for the training effort. Outline the training evaluation strategy and metrics. | Vacant | Application Development Group | IT PM/BusPM |  | Template |  |  | All sections of Training Plan have been completed. The individual in charge of completing deployment has reviewed the plan, and has no questions related to deployment. The project sponsor has accepted the plan. Training deployment is successful.
7.3 | OPERATIONS AND MAINTENANCE PLAN | This plan documents all ongoing activities necessary to operate and maintain the system in proper functioning condition. This plan includes a description of the resources required and their responsibilities, operational procedures for system startup and restart, backup and recovery, system archiving, and job scheduling. In addition, this plan addresses any training required by the user community in order to use the system and Service Level Agreement metrics associated with the system. | Development | Define operational procedures related to system startup, restart, backup, recovery and archiving. Determine resource planning needs. Map resource needs to operational procedures. Define ongoing training requirements for end-users, and resources maintaining system. Write a Service Level Agreement. Complete the Operations and Maintenance plan. | Mayra Toledo | Application Development Group | IT PM |  | Template |  |  | All fields of the Operations and Maintenance Plan have been completed and validated for quality and accuracy. System operations and maintenance is properly functioning, with resources aware of their responsibilities, and completing those tasks during ongoing maintenance, and in the case of any necessary system updates.
7.4 | TECHNICAL STAGE GATE 4: PRODUCTION READINESS REVIEW BRIEFING | Production Readiness Review includes a review of test results, changes to the security posture of the system, and activities that have been completed to prepare a system release for implementation. PRR is the final management decision point before a system release is implemented. There is a PowerPoint presentation template for those going through PRR, and a checklist template. | Testing | Complete PRR Presentation (including a review of Business Drivers, Schedule, Open Risks, Test Results, Security Impacts, Communication to End Users, Implementation Plans, and a high-level discussion of lessons learned). Obtain formal sign-off from business and technology organizations needed to support implementation of the system release. | Trey Wiesenburg | Enterprise Quality & Technical Change Management Group | IT PM |  | Template |  |  | Management acceptance of any outstanding risks associated with implementing the system release. Business and technology organizations agree that the necessary resources are in place to support implementation of the system release.
8 | POST-IMPLEMENTATION
8.1 | OPERATIONAL ANALYSIS | An Operational Analysis examines the on-going performance of an operation (capital assets). | Operations & Maintenance | Review program metrics and conduct market research to determine if customer satisfaction, contribution to strategic goals and mission of FSA, financial performance, and is the current investment still the most effective means of meeting the mission. | Daria Adams | ePMO | Program Manager |  | Template |  |  | The analysis answers the key questions of: Could the investment's objectives be better met; could costs be reduced; and should the organization continue performing this function. Results are reviewed by the program and the IRB for final determination on need for action.
8.2 | RETIREMENT AND DISPOSAL ARTIFACTS
8.2.1 | System Retirement Plan | The System Retirement Plan describes the system retirement strategy, the solution replacement and retirement requirements list, and the data/documentation plan. | Retirement | Define the system retirement strategy, document the requirements necessary prior to retirement, which include solution replacement if applicable. Complete System Retirement Plan. | Larry Lanwehr | Infrastructure Operations Group | IT PM |  | Template |  |  | Stage Gate Review Body acceptance of artifacts.
8.2.2 | System Disposal Plan | The System Disposal Plan documents the data that needs to be preserved when the system is disposed of, the timeline for the disposal activities, the software components and data to be preserved, the equipment and software disposal plan, the security measures to be taken to dispose of the system and its data, and the archival of lifecycle products. | Retirement | Document data that needs to be preserved, software disposal plan, and security and privacy measures after system disposal. Complete system disposal plan. | Larry Lanwehr | Infrastructure Operations Group | IT PM |  | Template |  |  | Stage Gate Review Body acceptance of artifacts.
8.3 | TECHNICAL STAGE GATE 5: RETIREMENT AND DISPOSAL REVIEW BRIEFING | Technical Stage Gate 5 ensures that a system and the system components are properly retired, sanitized, decommissioned, and archived according to NIST, Department of Education, and FSA guidelines, policies, standards, and procedures before passing from operations and maintenance into retirement. | Retirement | IPT meets with the Stage Gate Review Body and reviews the process inputs (those include the System Retirement and System Disposal Plans) and artifacts submitted by the IPT to assess whether the system is ready to be retired. | Larry Lanwehr | Infrastructure Operations Group | IT PM |  | Template |  |  | Stage Gate Review Body recommends project to move to the retirement stage.
[5 empty] | Creating Document |  |  |  |  | 0
[5 empty] | Updating Existing Document |  |  |  |  | 0
[5 empty] | Part of Another Document |  |  |  |  | 0
[5 empty] | Not Applicable |  |  |  |  | 0
[7 empty] | Total Artifacts That Apply | Total Artifacts That Apply |  | 0
[7 empty] | Total Artifacts Accounted For | Total Artifacts Accounted For |  | 0

## LMM Stage (hidden)
WBS Code | Element Name | Lifecycle Stage
1.1 | Project Initiation Artifacts | Vision
1.1.1 | Investment Request | Vision
1.1.2 | Business Case/Exhibit 300 | Vision
1.1.3 | Project Charter | Vision
1.2 | Project Management Plan Artifacts | Vision
1.2.1 | Lifecycle Management Methodology (LMM) Work Breakdown Structure Dictionary and Tailoring Plan | Vision
1.2.2 | Scope Management Plan | Vision
1.2.3 | Cost Management Plan | Vision
1.2.4 | Risk Management Plan | Vision
1.2.5 | Quality Management Plan | Vision
1.2.6 | Resource Management Plan | Vision
1.2.7 | Schedule Management Plan and Schedule | Vision
1.2.8 | Communication Management Plan | Vision
1.2.9 | Change Management Plan | Vision
1.2.10 | Independent Verification and Validation Plan | Vision
1.2.11 | Performance Management Plan | All
1.3 | Project Monitoring Artifacts | All
1.3.1 | Performance Reports | All
1.3.2 | Baseline Change Control Report | All
1.3.3 | Lessons Learned Reports | All
1.3.4 | Cost Estimate and Spend Report | All
1.3.5 | Risk Log | All
1.3.6 | Project Schedule | All
1.3.7 | Action and Issue Log | Vision
1.4 | Management Stage Gate 1: Investment Review Briefing | Definition
1.5 | Management Stage Gate 2: Requirements Review Briefing | Implementation
1.6 | Management Stage Gate 3: Project Closeout Review Briefing | Vision
2.1 | Acquisition Strategy | Definition
2.2 | Pre-Award Artifacts
2.2.1 | Statement of Need | Vision
2.2.2 | Market Research Report | Definition
2.2.3 | Acquisition Plan | Definition
2.2.4 | Statement of Objectives or Performance Work Statement | Definition
2.2.5 | Source Selection Plan | Definition
2.2.6 | Solicitation | Development
2.3 | Post-Award Artifacts
2.3.1 | Contract | Development
2.3.2 | Performance Monitoring Plan | Definition
3.1 | Information System Security Officer Appointment Letter | Definition
3.2 | Privacy Artifacts | Vision
3.2.1 | Privacy Threshold Analysis | Vision
3.2.2 | Privacy Impact Assessment | Definition
3.2.3 | System of Records Notice (SORN) | Definition
3.3 | External Data Exchange Artifacts | Definition
3.3.1 | Memorandum of Understanding | Development
3.3.2 | Computer Matching Agreement | Development
3.3.3 | Interconnection Security Agreement (ISA) | Implementation
3.4 | Continuity of Services Artifacts | Implementation
3.4.1 | Business Impact Analysis (BIA) | Implementation
3.4.2 | Information Technology (IT) Contingency Plan (Includes Test Plan) | Implementation
3.4.3 | Contingency Test Plan Results | Implementation
3.4.4 | Disaster Recovery Plan | Definition
3.5 | System Security Documentation Artifacts | Vision
3.5.1 | Data Sensitivity Worksheet | Definition
3.5.2 | System Boundary Template (System Authorization Boundary) | Definition
3.5.3 | System Security Plan | Development
3.6 | Security Risk Assessment Artifacts | Development
3.6.1 | Security Assessment Plan | Development
3.6.2 | System Security Documentation Checklists | Development
3.6.3 | Security Assessment Report | O&M
3.6.4 | Plans of Actions and Milestones (POAMs) | Testing
3.6.5 | Risk Analysis Form | Testing
3.7 | Authority to Operate Letter and Briefing | O&M
3.8 | Security, Certification & Accreditation & Post Implementation Evaluation Report | Vision
3.9 | Data Retention Schedule | Vision
4.1 | Initiative Vision Document | Vision
4.2 | Requirements Management Plan | Vision
4.3 | High Level Requirements Document | Definition
4.4 | User Interface (UI) Specification Document | Definition
4.5 | Detailed Requirements Document | Development
4.6 | Requirements Traceability Matrix | Definition
4.7 | Data Migration Plan | Definition
4.8 | Technical Stage Gate 3: Requirements Review Briefing | Definition
5.1 | Configuration Management Plan | Development
5.2 | Preliminary Design Document | Development
5.3 | Detailed Design Document | Development
5.4 | Solution Source Code and Deployable Artifacts | Testing
5.5 | Solution User Manual | Testing
5.6 | Release Version Description Document | Development
5.7 | Technical Stage Gates 1A and 1B: Engineering Review Board (ERB) Review Briefing | Development
5.8 | Technical Stage Gate 2: Test Readiness Review Briefing | Definition
6.1 | Master Test Plan | Definition
6.2 | Test Suites | Testing
6.3 | Test Reports | Testing
6.3.1 | User Acceptance Test Summary Report | Testing
6.3.2 | Test Summary Report | Testing
6.3.3 | Defect Management Report | Definition
7.1 | Implementation/ Transition Management Plan Artifacts | Definition
7.1.1 | Implementation Plan | Definition
7.1.2 | Transition Management Plan | Development
7.2 | Training Plan | Development
7.3 | Operations and Maintenance Plan | Testing
7.4 | Technical Stage Gate 4: Production Readiness Review Briefing | O&M
8.1 | Operational Analysis | Retirement
8.2 | Retirement and Disposal Artifacts | Retirement
8.2.1 | System Retirement Plan | Retirement
8.2.2 | System Disposal Plan | Retirement
8.3 | Technical Stage Gate 5: Retirement and Disposal Review Briefing | Retirement

## Labels (hidden)
Row Labels | Row Labels
All | All
Lessons Learned Reports | Lessons Learned Reports
Performance Reports | Performance Reports
Performance Management Plan | Performance Management Plan
Baseline Change Control Report | Baseline Change Control Report
Cost Estimate and Spend Report | Cost Estimate and Spend Report
Risk Log | Risk Log
Project Schedule | Project Schedule
Project Monitoring Artifacts | Project Monitoring Artifacts
Definition | Definition
Acquisition Plan | Acquisition Plan
Acquisition Strategy | Acquisition Strategy
Market Research Report | Data Migration Plan
Statement of Objectives or Performance Work Statement | Master Test Plan
Source Selection Plan | Requirements Traceability Matrix
Performance Monitoring Plan | Market Research Report
System Security Officer Appointment Letter | Statement of Objectives or Performance Work Statement
Privacy Impact Assessment | Source Selection Plan
System of Records Notice (SORN) | Performance Monitoring Plan
Disaster Recovery Plan | Privacy Impact Assessment
Data Sensitivity Worksheet | System of Records Notice (SORN)
System Boundary Template (System Authorization Boundary) | Disaster Recovery Plan
Management Stage Gate 1: Investment Review Briefing | Data Sensitivity Worksheet
External Data Exchange Artifacts | System Boundary Template (System Authorization Boundary)
Development | High Level Requirements Document
Contract | User Interface (UI) Specification Document
Solicitation | Defect Management Report
Memorandum of Understanding | Implementation Plan
System Security Plan | Management Stage Gate 1: Investment Review Briefing
Computer Matching Agreement | External Data Exchange Artifacts
Security Assessment Plan | Technical Stage Gate 3: Requirements Review Briefing
Security Risk Assessment Artifacts | Technical Stage Gate 2: Test Readiness Review Briefing
Implementation | Implementation/ Transition Management Plan Artifacts
Business Impact Analysis (BIA) | Information System Security Officer Appointment Letter
Contingency Test Plan Results | Development
Interconnection Security Agreement (ISA) | Configuration Management Plan
Information Technology (IT) Contingency Plan (Includes Test Plan) | Contract
Management Stage Gate 2: Requirements Review Briefing | Detailed Design Document
Continuity of Services Artifacts | Detailed Requirements Document
Vision | Preliminary Design Document
Change Management Plan | Solicitation
Communication Management Plan | Training Plan
Cost Management Plan | Memorandum of Understanding
Quality Management Plan | Computer Matching Agreement
Resource Management Plan | System Security Plan
Risk Management Plan | Security Assessment Plan
Schedule Management Plan and Schedule | System Security Documentation Checklists
Scope Management Plan | Release Version Description Document
Statement of Need | Transition Management Plan
Project Charter | Security Risk Assessment Artifacts
Lifecycle Management Methodology (LMM) Tailoring Plan | Technical Stage Gates 1A and 1B: Engineering Review Board (ERB) Review Briefing
Independent Verification and Validation Plan | Implementation
Action and Issue Log | Interconnection Security Agreement (ISA)
Privacy Threshold Analysis | Business Impact Analysis (BIA)
Investment Request | Information Technology (IT) Contingency Plan (Includes Test Plan)
Project Initiation Artifacts | Contingency Test Plan Results
Business Case/Exhibit 300 | Management Stage Gate 2: Requirements Review Briefing
Project Management Plan Artifacts | Continuity of Services Artifacts
Management Stage Gate 3: Project Closeout Review Briefing | O&M
Privacy Artifacts | Security Assessment Report
System Security Documentation Artifacts | Authority to Operate Letter and Briefing
(blank) | Technical Stage Gate 4: Production Readiness Review Briefing
Pre-Award Artifacts | Testing
Post-Award Artifacts | Operations and Maintenance Plan
Grand Total | Solution User Manual
Test Reports
Test Suites
Plans of Actions and Milestones (POAMs)
Risk Analysis Form
User Acceptance Test Summary Report
Test Summary Report
Solution Source Code and Deployable Artifacts
Vision
Change Management Plan
Communication Management Plan
Cost Management Plan
Initiative Vision Document
Quality Management Plan
Requirements Management Plan
Resource Management Plan
Risk Management Plan
Schedule Management Plan and Schedule
Scope Management Plan
Statement of Need
Investment Request
Project Charter
Independent Verification and Validation Plan
Action and Issue Log
Privacy Threshold Analysis
Security, Certification & Accreditation & Post Implementation Evaluation Report
Data Retention Schedule
Project Initiation Artifacts
Business Case/Exhibit 300
Project Management Plan Artifacts
Management Stage Gate 3: Project Closeout Review Briefing
Privacy Artifacts
System Security Documentation Artifacts
Lifecycle Management Methodology (LMM) Work Breakdown Structure Dictionary and Tailoring Plan
(blank)
Pre-Award Artifacts
Post-Award Artifacts
Retirement
Operational Analysis
System Retirement Plan
System Disposal Plan
Retirement and Disposal Artifacts
Grand Total